## Slide 1: Tribal Public Health Data Advancement Toolkit
U.S. Centers for Disease Control and Prevention
Prioritization Template
Please delete this slide after reviewing and applying the instructions throughout the template.

## Slide 2: Overview*
The Prioritization Template is the third phase of the Tribal Public Health Data Advancement Toolkit. Tribal public health authorities or tribally designated public health authorities are asked to plan and prioritize opportunities identified in the Data Modernization Questionnaire by categorizing and ranking them using the Prioritization Template. Discussing the impact, effort, and timeline of each opportunity may be beneficial in gaining consensus on the most impactful activities.
Tribal public health authorities or tribally designated public health authorities are henceforth referred to as "tribes" for the remainder of this template.
*Please delete this slide after reviewing and applying the instructions throughout the template.
Mobilize
User Guide
Assess
Data Modernization Questionnaire
Plan & Prioritize
Prioritization Template
Communicate
Executive Summary Report Template
Contributor Contact Sheet
Notes: Please delete this slide after reviewing and applying the instructions throughout the template.
Please Note: User guidance can be found within the notes on each slide.

## Slide 3: Overview Continued*
The Prioritization Template is meant to facilitate dialogue around opportunities identified within the Data Modernization Questionnaire. This template aims to have tribes reflect on actionable items based on their opportunities. The Prioritization Template includes three tools and associated guidance. Tools include:
Impact-Effort Matrix: An impact-effort matrix is a decision-making tool tribes can use to prioritize opportunities based on their potential impact and the amount of effort required to implement them.
Action Planning templates: As a next step, tribes will identify specific actions for each prioritized topic area.
Timeline template: After completing the action planning exercise, tribes are encouraged to discuss the start date of each opportunity and label it as either short-, intermediate-, or long-term.
Tribes are encouraged to complete this template collaboratively, using their Data Modernization Questionnaire responses as a baseline for discussion. Tribes can use these templates by deleting the title and overview slides before branding the remaining template slides as their own. Additional notes and guidance can be found in the Notes section of this slide deck.
*Please delete this slide after reviewing and applying the instructions throughout the template.
Notes: Please delete this slide after reviewing and applying the instructions throughout the template.
Please Note: User guidance can be found within the notes on each slide.
NOTE: Tribal public health authorities or tribally designated public health authorities are henceforth referred to as "tribes" for the remainder of this document.

## Slide 4: Tribe Name Public Health Data Advancement Toolkit: Prioritization Template
Date: XX/XX/XXXX
Notes: The PowerPoint template does not use specific branding to allow for customization by each Tribal public health authority. Feel free to change the colors and backgrounds of these slides or input the information in a branded slide deck.
NOTE: For the rest of the slide deck, when Tribes are mentioned, it refers to Tribal public health authorities.
Suggested Edits:
Replace the highlighted text with your Tribe’s name.
Replace the date with today’s date or the presentation date.

## Slide 5: Introduction
Prioritization materials can be a helpful tool for categorizing and ranking potential opportunities. Given limited time and resources, making informed decisions about which opportunities to pursue is critical for success. Additionally, the proper sequencing of opportunities can optimize resource allocation and support the completion of larger initiatives with interdependencies.
These prioritization materials are meant to facilitate dialogue around opportunities identified within the Data Modernization Questionnaire: Enterprise-wide Structures and Data Modernization Questionnaire: Program Structures. This will support tribal public health authorities align on high-level data modernization priorities and associated actions.
Prioritization materials can be a helpful tool for categorizing and ranking potential opportunities. Given limited time and resources, making informed decisions about which opportunities to pursue is critical for success. Additionally, the proper sequencing of opportunities can optimize resource allocation and support the completion of larger initiatives with interdependencies.
These prioritization materials are meant to facilitate dialogue around opportunities identified within the Data Modernization Questionnaire: Enterprise-wide Structures and Data Modernization Questionnaire: Program Structures. This will support tribal public health authorities align on high-level data modernization priorities and associated actions.
5
Notes: NOTE: When “Tribes” are referenced throughout the remainder of the slide deck, it refers to tribal public health authorities.

## Slide 6: Prioritization Template Overview
The Tribal Public Health Data Advancement Toolkit includes the following tools:
The Tribal Public Health Data Advancement Toolkit includes the following tools:
Impact-Effort Matrix
  Decision-making tool tribes can use to prioritize opportunities based on their potential impact and the amount of effort required to implement them.
  Tribes are encouraged to start by discussing high-level data modernization topics (e.g., data governance, IT governance, workforce, etc.).
Action Planning Templates
  Templates to help tribes identify specific actions for each prioritized data modernization topic.
  Tribes are encouraged to complete this activity after the impact-effort matrix, once they have a better understanding of their high-level data modernization priorities.
Timeline Template
  Decision-making tool tribes can use to determine the start date of prioritized actions.
  Tribes are encouraged to use this template to discuss and identify the start date for prioritized actions.
3
2
Decision-making tool tribes can use to prioritize opportunities based on their potential impact and the amount of effort required to implement them.
Tribes are encouraged to start by discussing high-level data modernization topics (e.g., data governance, IT governance, workforce, etc.).
Templates to help tribes identify specific actions for each prioritized data modernization topic.
Tribes are encouraged to complete this activity after the impact-effort matrix, once they have a better understanding of their high-level data modernization priorities.
Decision-making tool tribes can use to determine the start date of prioritized actions.
Tribes are encouraged to use this template to discuss and identify the start date for prioritized actions.
1
  Impact-Effort Matrix
  Action Planning Templates
  Timeline Template
6

## Slide 7: Completing the Prioritization Template
The prioritization template will likely require multiple working sessions to complete. It is recommended that you schedule at least one one-hour working session per tool. However, tribes may establish a meeting cadence that best aligns with their needs and preferences. Representative process steps to prepare for, execute, and follow-up about each meeting include:
The prioritization template will likely require multiple working sessions to complete. It is recommended that you schedule at least one one-hour working session per tool. However, tribes may establish a meeting cadence that best aligns with their needs and preferences. Representative process steps to prepare for, execute, and follow-up about each meeting include:
Before Each Meeting:
Step 1: Identify key roles and responsibilities
Step 2: Send out read-ahead materials (e.g., completed Data Modernization Questionnaire)
Step 3: Tailor templates as needed
During Each Meeting:
Step 4: Facilitate discussion and plot “post-its” accordingly
Step 5: Review “post-it” placements and make final updates as needed
Step 6: Capture key takeaways, decisions, and action items within a detailed meeting summary
After Each Meeting:
Step 7: Share meeting summary and facilitation slides with participants
Step 8: Gather feedback on meeting format, content, and effectiveness to make improvements if necessary
Step 9: Schedule follow-up meetings as needed, and share information on next steps
Before Each Meeting:
During Each Meeting:
After Each Meeting:
Step 1: Identify key roles and responsibilities
Step 2: Send out read-ahead materials (e.g., completed Data Modernization Questionnaire)
Step 3: Tailor templates as needed
Step 4: Facilitate discussion and plot “post-its” accordingly
Step 5: Review “post-it” placements and make final updates as needed
Step 6: Capture key takeaways, decisions, and action items within a detailed meeting summary
Step 7: Share meeting summary and facilitation slides with participants
Step 8: Gather feedback on meeting format, content, and effectiveness to make improvements if necessary
Step 9: Schedule follow-up meetings as needed, and share information on next steps
7

## Slide 8: Completing the Prioritization Template: Roles
Representative roles and responsibilities for each meeting may include:
Representative roles and responsibilities for each meeting may include:
Role | Responsibilities
Facilitator | Facilitate open and respectful dialogue. Encourage active participation from all meeting participants. Keep discussions on track and aligned with the agenda.
Presenter | Share screen during the meeting. Make live updates to slides based on discussion. Set up and test screen sharing tool before the meeting.
Note Taker | Record key takeaways, decisions, and actions. Seek clarification from participants as needed. Distribute meeting notes to participants.
Meeting Participants | Review agenda and read-ahead materials before meeting. Contribute to discussions, share insights, and ask questions. Communicate respectfully and listen actively to others.
Collaboration Site Administrator | Set up a collaboration site (e.g., Microsoft Teams, SharePoint). Add, modify, or remove users from the collaboration site as needed. Monitor version control for documents and files.
8

## Slide 9: Impact-Effort Matrix: Overview
Step 1
Step 1 An impact-effort matrix is a decision-making tool tribes can use to prioritize opportunities based on their potential impact and the amount of effort required to implement them. The impact of an opportunity is typically measured in terms of its ability to achieve data advancement objectives. The effort required to implement an opportunity is measured in terms of time, money, or other resources. Based on their impact and effort, opportunities can be mapped to one of the following quadrants:
Quick Wins (high impact/low effort): These represent the best opportunities for tribes – low effort and high reward. Tribes should consider placing the highest priority on opportunities in this quadrant.
Incremental (low impact/low effort): While these opportunities take little effort, tribes should consider sequencing these after more rewarding opportunities are addressed.
Rethink (low impact/high effort): Opportunities that fall in those grid quadrants may not become priorities. Tribes may want to determine whether they are worth doing at all.
Major Projects (high impact/high effort): These are great opportunities for tribes but require a higher level of effort. Tribes may want to consider these opportunities if the organization is fully committed to completing the hard work involved over the long haul.
Instructional Note: To complete the impact-effort matrix, tribes can use the pre-populated “post-its” on slide 8 that contain topic areas covered in the Data Modernization Questionnaire or tribes can create their own “post-it” pertaining to a unique topic area of their choosing. During a facilitated discussion, tribes can determine the impact and effort of implementing opportunities within each topic area and plot each “post-it” on the graph accordingly. Tribes are encouraged to move forward with 3-5 well-defined topic areas.
An impact-effort matrix is a decision-making tool tribes can use to prioritize opportunities based on their potential impact and the amount of effort required to implement them. The impact of an opportunity is typically measured in terms of its ability to achieve data advancement objectives. The effort required to implement an opportunity is measured in terms of time, money, or other resources. Based on their impact and effort, opportunities can be mapped to one of the following quadrants:
Quick Wins (high impact/low effort): These represent the best opportunities for tribes – low effort and high reward. Tribes should consider placing the highest priority on opportunities in this quadrant.
Incremental (low impact/low effort): While these opportunities take little effort, tribes should consider sequencing these after more rewarding opportunities are addressed.
Rethink (low impact/high effort): Opportunities that fall in those grid quadrants may not become priorities. Tribes may want to determine whether they are worth doing at all.
Major Projects (high impact/high effort): These are great opportunities for tribes but require a higher level of effort. Tribes may want to consider these opportunities if the organization is fully committed to completing the hard work involved over the long haul.
Instructional Note: To complete the impact-effort matrix, tribes can use the pre-populated “post-its” on slide 8 that contain topic areas covered in the Data Modernization Questionnaire or tribes can create their own “post-it” pertaining to a unique topic area of their choosing. During a facilitated discussion, tribes can determine the impact and effort of implementing opportunities within each topic area and plot each “post-it” on the graph accordingly. Tribes are encouraged to move forward with 3-5 well-defined topic areas.
9

## Slide 10: Impact-Effort Matrix: Facilitation Questions
Step 1
Step 1
To what extent do opportunities in this topic area align with our organization’s goals and objectives?
What positive outcomes will result from implementing opportunities in this topic area?
Who are the primary beneficiaries of opportunities in this topic area?
Could opportunities in this topic area be coordinated across multiple program areas or public health activities?
Would opportunities in this topic area align with our organization’s existing strengths and capabilities?
What resources are required to implement opportunities in this topic area?
Do we have the necessary skills and capabilities to execute opportunities in this topic area effectively?
What are the potential obstacles or risks associated with opportunities in this topic area?
To what extent are opportunities in the topic area pre-requisites for other priority efforts?
To what extent do opportunities in this topic area align with our organization’s goals and objectives?
What positive outcomes will result from implementing opportunities in this topic area?
Who are the primary beneficiaries of opportunities in this topic area?
Could opportunities in this topic area be coordinated across multiple program areas or public health activities?
Would opportunities in this topic area align with our organization’s existing strengths and capabilities?
What resources are required to implement opportunities in this topic area?
Do we have the necessary skills and capabilities to execute opportunities in this topic area effectively?
What are the potential obstacles or risks associated with opportunities in this topic area?
To what extent are opportunities in the topic area pre-requisites for other priority efforts?
10

## Slide 11: Impact-Effort Matrix
Quick Wins
Major Projects
Incremental
Rethink
Quick Wins
Major Projects
Incremental
Rethink
Effort
Impact
High
Low
Low
High
11
Data Governance Structure
Data Governance Processes
Data Governance Structure
Data Analytics
Data Governance Structure
Data Privacy
Data Governance Structure
External Data Sharing
IT Governance Structure
IT Management
IT Governance Structure
Information Security and Cybersecurity
External Policy
External Legal or Regulatory Requirements
Technology
System Interoperability
Technology
IT Infrastructure
Technology
User Interface/User Experience (UI/UX)
Workforce
Workforce Recruitment and Employee Onboarding
Data Governance Structure
Data Standards
Data Governance Structure
Data Architecture
Data Governance Structure
Data Quality and Management
Data Governance Structure
Internal Data Sharing
IT Governance Structure
IT Standards
IT Governance Structure
IT Governance Processes
External Policy
External Compliance Requirements
Technology
Data Repository
Technology
System Development and Improvement
Workforce
Workforce Learning and Development
Workforce
Workforce Retention
Other
Notes: Pre-populated “post-its” can be found just below the slide in the grey space. Use the zoom function to view the pre-populated “post-its”.
Impact-Effort Matrix: Facilitation Questions
To what extent do opportunities in this topic area align with our organization’s goals and objectives?
What positive outcomes will result from implementing opportunities in this topic area?
Who are the primary beneficiaries of opportunities in this topic area?
Could opportunities in this topic area be coordinated across multiple program areas or public health activities?
Would opportunities in this topic area align with our organization’s existing strengths and capabilities?
What resources are required to implement opportunities in this topic area?
Do we have the necessary skills and capabilities to execute opportunities in this topic area effectively?
What are the potential obstacles or risks associated with opportunities in this topic area?
To what extent are opportunities in the topic area pre-requisites for other priority efforts?

## Slide 12: Action Planning: Overview
Step 2
Step 2
After completing the impact-effort matrix, tribes should have a better understanding of their high-level data modernization priorities. As a next step, tribes will identify specific actions for each prioritized topic area.
The following action planning templates contain pre-populated “post-its”, with opportunities pulled directly from the Data Modernization Questionnaire. Using these templates or creating their own opportunity “post-it”, tribes will determine their most significant opportunities based on value, urgency, and feasibility, among other criteria determined by the tribe.
Tribes are encouraged to move forward with 3-5 well-defined opportunities per topic area.
After completing the impact-effort matrix, tribes should have a better understanding of their high-level data modernization priorities. As a next step, tribes will identify specific actions for each prioritized topic area.
The following action planning templates contain pre-populated “post-its”, with opportunities pulled directly from the Data Modernization Questionnaire. Using these templates or creating their own opportunity “post-it”, tribes will determine their most significant opportunities based on value, urgency, and feasibility, among other criteria determined by the tribe.
Tribes are encouraged to move forward with 3-5 well-defined opportunities per topic area.

## Slide 13: Action Planning: Facilitation Questions
Step 2
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?
13

## Slide 14: Data Governance Processes
Prioritized Opportunities:
Opportunities:
Establish, document, and implement an organization-wide data governance process to guide our tribe’s major data decisions.
Develop strategies to prioritize data governance within our tribe (e.g., establishing workgroups to champion data governance).
Include information security and cybersecurity as core priorities and activities in our IT and data governance and strategies.
Define and communicate the advantages, limitations, impacts, and opportunities of data governance processes to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on data governance processes.
Designate an individual/group of people to oversee data governance (e.g., data governance committee, Chief Data Officer, etc.).
Other.
Prioritized Opportunities:
Opportunities:
Establish, document, and implement an organization-wide data governance process to guide our tribe’s major data decisions.
Develop strategies to prioritize data governance within our tribe (e.g., establishing workgroups to champion data governance).
Include information security and cybersecurity as core priorities and activities in our IT and data governance and strategies.
Define and communicate the advantages, limitations, impacts, and opportunities of data governance processes to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on data governance processes.
Designate an individual/group of people to oversee data governance (e.g., data governance committee, Chief Data Officer, etc.).
Other.
14
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 15: Data Standards
Prioritized Opportunities:
Opportunities:
Adopt terminology consistent with nationally recognized clinical/public health data systems, if applicable (e.g., LOINC, SNOMED, ICD, CPT, CVX, CDC PHIN VADS).
Adopt nationally recognized health message/content standards, if applicable (e.g., HL7 version 2, CDA, or FHIR).
Define and communicate the advantages, limitations, impacts, and opportunities for implementing data standards to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on data standards.
Other
Prioritized Opportunities:
Opportunities:
Adopt terminology consistent with nationally recognized clinical/public health data systems, if applicable (e.g., LOINC, SNOMED, ICD, CPT, CVX, CDC PHIN VADS).
Adopt nationally recognized health message/content standards, if applicable (e.g., HL7 version 2, CDA, or FHIR).
Define and communicate the advantages, limitations, impacts, and opportunities for implementing data standards to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on data standards.
Other.
15
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 16: Data Architecture
Prioritized Opportunities:
Opportunities:
Utilize message or data integration services (e.g., integration engines) to enable the electronic bidirectional exchange of data between our tribal public health data systems and external data providers (e.g., state health department, county health department, Tribal Epidemiology Centers (TECs)).
Utilize data engineering processes (e.g., extract-transform-load or extract-load-transform processes) to enable the transformation and mapping of varied and unstructured data into a unified structured or semi-structured data model.
Define and communicate the advantages, limitations, impacts, and opportunities for implementing data architecture to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on data architecture.
Other.
16
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 17: Data Quality and Management
Prioritized Opportunities:
Opportunities:
Establish and standardize policy or protocols to manage data quality such as timeliness, completeness, and accuracy.
Establish and standardize policy or protocols to manage our data lifecycle (e.g., data creation or collection, management, usage such as publication, data sharing, retention policies and system backups, and disposition of records).
Establish a data management framework, including governance, processes, standards, and technology, that unifies our tribal data.
Define and communicate the advantages, limitations, impacts, and opportunities for improved data quality and management to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on data quality and management.
Other.
17
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 18: Internal Data Sharing
Prioritized Opportunities:
Opportunities:
Establish and standardize policies and protocols governing data sharing and exchange internally (e.g., Tribal Resolutions, MOUs, DUAs, and BAAs among our public health programs or our broader tribal health organization).
Adopt a standard procedure for establishing, monitoring, and renewing Tribal Resolutions, MOUs, DUAs, and/or BAAs with internal partners.
Define and communicate the advantages, limitations, impacts, and opportunities for internal data sharing to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on internal data sharing.
Other.
18
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 19: External Data Sharing
Prioritized Opportunities:
Opportunities:
Establish and standardize policies and protocols (e.g., MOUs, DUAs and BAAs), governing data sharing and exchange with external partners (e.g., state health department, county health department, TECs)
Adopt a standard procedure for establishing, monitoring, and renewing MOUs, DUAs, and/or BAAs with external partners.
Build, enhance, and continuously monitor relationships with external partners to support data sharing and exchange.
Define and communicate the advantages, limitations, impacts, and opportunities for external data sharing to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on external data sharing.
Other.
19
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 20: Data Privacy
Prioritized Opportunities:
Opportunities:
Establish internal and external data policies and protocols to ensure confidentiality and informed consent.
Establish policies to preserve privacy when publishing or reporting data, such as not publishing data for small population groupings (e.g., small numbers policy).
Establish mechanisms for data sharing that provide secure access to identified and/or deidentified data both internally and externally.
Define and communicate the advantages, limitations, impacts, and opportunities for data privacy to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on data privacy.
Other.
20
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 21: Data Analytics
Prioritized Opportunities:
Opportunities:
Identify and leverage existing data analytics activities within our tribe to build new analytics and reporting opportunities.
Share aggregated data analytics, outputs, and reports with internal partners.
Share aggregated data analytics, outputs, and reports with external partners.
Share aggregated data analytics, outputs, and reports on public-facing channels (e.g., website, social media, etc.).
Utilize data analytics and data-driven decision making to inform our public health activities.
Define and communicate the advantages, limitations, impacts, and opportunities for data analytics to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on the spectrum of data analytics methods and relevant applications in public health.
Other.
21
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 22: IT Governance Processes
Prioritized Opportunities:
Opportunities:
Establish an IT governance process to guide major information and system decisions.
Establish standard processes to guide technology investment decisions, such as “buy versus build” and reducing redundant services.
Establish an innovation or technology improvement strategy to promote and govern our technology innovation efforts.
Define and communicate the advantages, limitations, impacts, and opportunities for implementing IT governance to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on IT governance processes.
Designate an individual/group of people to oversee IT governance.
Other.
22
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 23: IT Standards
Prioritized Opportunities:
Opportunities:
Establish processes to identify, adopt, and use IT standards across our organization.
Identify, prioritize, and implement additional IT standards to complement those currently in place.
Collaborate with public health programs and staff to identify ways to implement IT standards with minimal disruption to activities.
Develop enterprise-wide communications about IT standards.
Define and communicate the advantages, limitations, impacts, and opportunities for implementing IT standards to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to tribal staff on IT standards.
Other.
23
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 24: IT Management
Prioritized Opportunities:
Opportunities:
Conduct an inventory of our data sets, applications, and information systems. This can include a digital IT asset inventory management process to dynamically catalog and manage hardware and software assets, licenses, networks/network devices, configuration, processes, documentation, and other Health Information Technology (HIT) resources.
Establish processes, in collaboration with programs, for granting and managing user accounts and access to systems.
Establish and implement processes to monitor and manage our IT systems and resources, such as adopting Information Technology Infrastructure Library (ITIL) practices, implementing an IT Service Management support desk, etc.
Include IT management processes as core activities in our IT governance and strategies.
Define and communicate the advantages, limitations, impacts, and opportunities for implementing IT management to leadership and programs to get obtain buy-in.
Provide continuous learning and development opportunities to staff on IT management.
Develop frequent enterprise-wide communications about IT management so that the organization stays up to date on IT activities.
Other.
24
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 25: Cybersecurity
Prioritized Opportunities:
Sample Opportunities:
Establish processes to identify vulnerabilities, evaluate threats, and implement key security controls in software applications and/or apply system hardening techniques to improve the security and resiliency of our IT infrastructure.
Establish reporting mechanisms in the event of a suspected ransomware attack or data breach to initiate a response to limit damage.
Perform preventative processes to detect and mitigate security threats, performance issues, or non-compliance problems, such as CM, IV&V, risk assessment, security tabletop exercises, etc.
Include information security and cybersecurity as core priorities and activities in our IT and data governance and strategies.
Define and communicate the advantages, limitations, impacts, and opportunities for implementing information security and cybersecurity to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities and prevention tactics to staff on cybersecurity.
Develop frequent enterprise-wide communications and reports about cybersecurity threats, prevention, and monitoring.
Other.
25
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 26: External Legal or Regulatory Requirements
Prioritized Opportunities:
Opportunities:
Establish relationships and data sharing agreements to increase data accessibility and/or data quality (e.g., partnering with state/local health agencies, TECs, state health universities, health care providers).
Establish relationships that facilitate partnering on data policy development or revision (e.g., with state/local health agencies, TECs, state health universities) or participating in tribal-focused professional associations
Participate in efforts to enact policy change (e.g., attendance at committee hearings).
Engage with TECs, Tribal Liaison Officers, and other federal points of contact (e.g., IHS, 638 facilities, and CDC).
Provide continuous learning and development opportunities to staff on legal and regulatory requirements.
Other.
26
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 27: External Compliance Requirements
Prioritized Opportunities:
Opportunities:
Participate in tribal health boards, councils, or organizations.
Engage with TECs, Tribal Liaison Officers, and other federal points of contact (e.g., IHS, 638 facilities, and CDC).
Establish or enhance relationships with other tribes/tribal organizations to share best practices and experiences.
Establish or enhance relationships with state and/or local health agencies to share best practices and experiences.
Provide continuous learning and development opportunities to staff on compliance requirements.
Other.
27
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 28: IT Infrastructure
Prioritized Opportunities:
Opportunities:
Identify data sets, applications, information systems, and/or services that can be migrated to a cloud-based platform.
Evaluate the pros and cons of migrating our data sets, applications, and information systems to a cloud-based computing platform (e.g., cost-effectiveness, scalability, etc.) in collaboration with programs.
Develop and implement a cloud strategy and/or a cloud-first IT implementation roadmap [e.g., Infrastructure as a Service (IaaS); Platform as a Service (PaaS), or Software as a Service (SaaS)].
Develop standard operating procedures (SOPs) to be used in the event of power outages. This may include processes for storing hard copies of essential files to enable offline work.
Define and communicate the advantages, limitations, impacts, and opportunities for IT infrastructure, such as cloud, to leadership and programs to get buy-in.
Provide continuous learning and development opportunities to staff on IT infrastructure.
Other.
28
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 29: System Development and Improvement
Prioritized Opportunities:
Opportunities:
Develop and conduct processes for assessing systems development and improvement needs in collaboration with programs and data users.
Identify, document, collate, and prioritize overlapping system needs and requirements from users across programs.
Develop an enterprise-wide system development and improvement strategy roadmap for new and antiquated systems that incorporate user needs and requirements.
Identify system development lifecycle roles, responsibilities, and processes in which our IT and program staff should be involved.
Define and communicate the advantages, limitations, impacts, and opportunities for system development and improvement, such as cloud, to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on system development and improvement.
Other.
29
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 30: User Interface/User Experience (UI/UX)
Prioritized Opportunities:
Opportunities:
Identify and document staff’s barriers to using each system, including UI/UX limitations, unmet needs and requirements, ease of use, etc.
Establish communication channels (e.g., meetings, forums, or other mechanisms) for system users to regularly convey system roadblocks and recommend enhancements.
Conduct a gap analysis to identify systems’ current state versus desired future state (based on users’ needs/ requirements). Identify potential UI/UX solutions and priorities to evolve towards future state.
Define and communicate the advantages, limitations, impacts, and opportunities for system UI/UX enhancements (e.g., improved system utilization) to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on system features and capabilities, such as training using specific use case scenarios relevant to each program.
Provide continuous learning and development opportunities to staff on enhancing system user interface/experience (UI/UX).
Other.
30
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 31: System Interoperability
Prioritized Opportunities:
Opportunities:
Develop strategies for adopting and implementing nationally recognized vocabulary, messaging, and transport standards, if applicable.
Identify our stand-alone data systems that do not or cannot interoperate with internal other health or public health information systems.
Identify our stand-alone data systems that do not or cannot interoperate with external other health or public health information systems.
Identify barriers, opportunities, and technical strategies needed to electronically send, receive, and process data between internal data systems.
Identify barriers, opportunities, and technical strategies needed to electronically send, receive, and process data between external partner systems.
Collaborate across program areas to identify high-value external partners.
Coordinate with external partners to develop processes for electronically sending, receiving, and processing data with their systems.
Develop an Application Programming Interface (API) Strategy/API Management Plan to manage interface development and maintenance.
Define and communicate the advantages, limitations, impacts, and opportunities for system interoperability to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on system interoperability, including system interfaces (i.e., APIs) and nationally recognized vocabulary, messaging, and transport standards such as HL7.
Other.
31
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 32: Data Repository
Prioritized Opportunities:
Opportunities:
Collaborate with programs to identify enterprise-wide and program specific applications for implementing a centralized data repository.
Identify limitations of existing data repositories for tribal leadership and staff.
Establish a data lake (a centralized repository that allows storage of all structured and unstructured data at any scale).
Establish a data warehouse (a centralized data repository from one or more discrete sources).
Establish a data mart (a centralized repository of data that is oriented to a specific team).
Define and communicate the advantages, limitations, impacts, and opportunities for a centralized data repository to leadership and programs to obtain buy-in.
Provide continuous learning and development opportunities to staff on centralized data repositories.
Designate an individual/group of people to actively manage our data repository.
Other.
32
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 33: Workforce Learning and Development
Prioritized Opportunities:
Opportunities:
Leverage technical assistance support from Tribal Epidemiology Centers (TECS) or other State, Tribal, Local, or Territorial (STLT) organizations to support the identification of learning and development needs.
Increase availability of flexible learning opportunities for staff to complete on their own schedule, including online and free/low-cost training materials.
Conduct an environmental scan to identify available learning and development resources.
Develop and implement a communication plan to promote available learning and development opportunities to staff.
Deliver surveys before and after trainings to evaluate training effectiveness.
Define and communicate the advantages, limitations, impacts, and opportunities for workforce learning and development to leadership and programs to obtain buy-in.
Identify interested staff to participate in data-related communities of practice.
Create a community of practice across our tribe’s public health data partners
Other.
33
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 34: Workforce Recruitment and Employee Onboarding
Prioritized Opportunities:
Opportunities:
Create templates and standardize processes for the development of job descriptions.
Establish employee referral programs that incentivize staff for referring qualified candidates.
Improve the pipeline that supports the development of our tribe’s future public health workforce. This may include building partnerships with universities and schools of public health to bolster our tribal workforce.
Standardize processes for conducting interviews. This may include developing standard interview questions, implementing a skills test, and gathering feedback from candidates to continuously improve the interview process.
Assist with relocation expenses and/or housing assistance for new employees.
Standardize processes for employee onboarding. This may include developing an employee handbook, clearly documenting job roles and responsibilities, and conducting a comprehensive orientation.
Implement 30-60-90-day plans to set objectives for new employees in the first 3 months of their new position.
Other.
34
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 35: Workforce Retention
Prioritized Opportunities:
Opportunities:
Implement an employee mentoring program to support professional development and accelerate career growth.
Document and maintain in a centralized location job responsibilities and work processes that can be used during staffing transitions.
Increase opportunities for career growth and professional development. This may include opportunities for upward mobility, continued education, or skill advancement.
Conduct listening sessions for staff to provide feedback on employee experience and satisfaction.
Conduct exit interviews to identify organizational strengths/weaknesses and better understand reasons for staff turnover.
Implement recognition programs and/or incentives for staff to increase employee engagement.
Establish open lines of communication for staff to provide feedback on employee experience and satisfaction.
Implement flexible work schedules (e.g., four-day work week, workers having flexible arrival and departure times).
Implement remote positions.
Other.
35
Notes: Action Planning: Facilitation Questions
Which opportunities seem the most actionable and why?
What is the short-term value of this opportunity?
What is the long-term value of this opportunity?
Could this opportunity be coordinated across multiple program areas or public health activities?
Would this opportunity align with our organization’s existing strengths and capabilities?
Which opportunities are the most urgent and why?
To what extent is this opportunity a pre-requisite for other priority efforts?
What resources are required to implement this opportunity?
Do we have the necessary skills and capabilities to execute this opportunity effectively?
What are the potential obstacles or risks associated with this opportunity?

## Slide 36: Timeline Template: Overview
Step 3
Step 3
The timeline template is another a decision-making tool tribes can use to determine the start date of prioritized opportunities. After completing the action planning exercise, tribes are encouraged to discuss the start date of each opportunity and label it as either short-, intermediate-, or long-term. The template uses 0 - 1.5 years, 1.5 - 3 years, and 3+ years to define short-, intermediate-, and long-term. However, tribes are welcome to modify these definitions to better match their expected timelines.
To use the timeline, tribes can copy-paste prioritized opportunities from the action planning templates on slide 35. During a facilitated discussion, tribes are encouraged to determine the start date of each opportunity and plot it on the graph accordingly.
The timeline template is another a decision-making tool tribes can use to determine the start date of prioritized opportunities. After completing the action planning exercise, tribes are encouraged to discuss the start date of each opportunity and label it as either short-, intermediate-, or long-term. The template uses 0 - 1.5 years, 1.5 - 3 years, and 3+ years to define short-, intermediate-, and long-term. However, tribes are welcome to modify these definitions to better match their expected timelines.
To use the timeline, tribes can copy-paste prioritized opportunities from the action planning templates on slide 35. During a facilitated discussion, tribes are encouraged to determine the start date of each opportunity and plot it on the graph accordingly.
36

## Slide 37: Timeline Template: Facilitation Questions
Step 3
Step 3
Are there key milestones or critical steps that need to be accomplished before we can initiate selected opportunities?
What are the estimated resources requirements for each opportunity, and do we have a plan in place to ensure these resources are available when needed?
Are there any external factors (e.g., legal and regulatory) that we need to consider when determining start date?
Can we identify any potential risks that could impact the start date of each opportunity?
Are there key milestones or critical steps that need to be accomplished before we can initiate selected opportunities?
What are the estimated resources requirements for each opportunity, and do we have a plan in place to ensure these resources are available when needed?
Are there any external factors (e.g., legal and regulatory) that we need to consider when determining start date?
Can we identify any potential risks that could impact the start date of each opportunity?
37

## Slide 38: Timeline Template
Timeline
Short-term
(Kickoff within 1.5 years)
Intermediate-term
(Kickoff within 1.5 – 3 years)
Long-term
(Kickoff in 3+ years)
Short-term
(Kickoff within 1.5 years)
Intermediate-term
(Kickoff within 1.5 – 3 years)
Long-term
(Kickoff in 3+ years)
Timeline
Copy and paste prioritized opportunities from the action planning templates.
To copy and paste in PowerPoint, select desired content, press Ctrl+C (or Command+C on Mac), move to the desired location, and press Ctrl+V (or Command+V on Mac) to paste it.
38
Notes: Timeline Template: Facilitation Questions
Are there key milestones or critical steps that need to be accomplished before we can initiate selected opportunities?
What are the estimated resources requirements for each opportunity, and do we have a plan in place to ensure these resources are available when needed?
Are there any external factors (e.g., legal and regulatory) that we need to consider when determining start date?
Can we identify any potential risks that could impact the start date of each opportunity?