## Project schedule
| Gap Analysis ISO35001 | [8 empty] | Project start: | [7 empty] | 2024-02-27
[10 empty] | Display week: | [7 empty] | 1
[10 empty] | Display week: | [7 empty] | 1
| Develop of Documentation for Accident and Incident Investigation System | [8 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22 | [6 empty] | 2024-07-29 | [6 empty] | 2024-08-05 | [6 empty] | 2024-08-12 | [6 empty] | 2024-08-19 | [6 empty] | 2024-08-26 | [6 empty] | 2024-09-02
| TASK | ASSIGNED TO | Comments | Actual Finished date | PROGRESS | START |  | END | time axis 2024-02-26 to 2024-09-08
#day | time axis 2024-02-26 to 2024-09-08
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Define procedural needs for accident and incident reporting
| 1 Propose plan to IBC |  |  |  | 0% | 2024-01-29 | 5 | 2024-02-03 | 6
| 1.1. Prepare proposal |  |  |  | 0% | 2024-01-29 | 3 | 2024-02-01 | 4
| 1.2. Submit proposal to the IBBC members |  |  |  | 0% | 2024-01-29 | 1 | 2024-01-30 | 2
| 1.3. Schedule IBBC meeting |  |  |  | 0% | 2024-02-01 | 1 | 2024-02-02 | 2
| 1.4. Present proposal |  |  |  | 0% | 2024-02-01 | 1 | 2024-02-02
| 1.5. IBBC approve |  |  |  | 0% | 2024-02-01 | 1 | 2024-02-02
| 2. Select team for information gathering |  |  |  | 0% | 2024-01-22 | 1 | 2024-01-23
| 2.1. Assign team |  |  | 2025-01-25 | 100% | 2024-01-22 | 1 | 2024-01-23
| 2.2. Send appointment letter |  |  |  | 0% | 2024-01-29 | 1 | 2024-01-30
| 2.3. Team approve appointment |  |  |  | 0% | 2024-01-29 | 1 | 2024-01-30
| Accidents, incidents and near miss definition |  |  |  | 0% |  | 23 | 1900-01-22
| Conduct literature review |  |  |  | 100% | 2024-01-22 | 1 | 2024-01-23
| 3.1. Find references |  |  | 2024-01-25 | 100% | 2024-01-22 | 1 | 2024-01-23
| 3.1.1. Cross check documents and legal binding documents |  |  |  | 0% | 2024-02-05 | 6 | 2024-02-11
| 3.2. Read & study reference document |  |  |  | 0% | 2024-02-05 | 2 | 2024-02-07
| 3.3. Compile material data |  |  |  | 0% | 2024-02-07 | 2 | 2024-02-09
| 3.4. Summarise information/data - List of reference, info & data |  |  |  | 0% | 2024-02-09 | 2 | 2024-02-11
| Accident, incident, near miss definition |  |  |  | 0% | 2024-02-05 | 5 | 2024-02-10
| 3.5. Schedule discussion |  |  |  | 0% | 2024-02-05 | 3 | 2024-02-08
| 3.6. Finalise information |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| Severity of accidents/ incidents categorisation |  |  |  | 0% | 2024-01-29 | 10 | 2024-02-08
| 4.1. Find reference |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| 4.2. Read & study documents |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| 4.3. Compile documents |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| 4.4. Summarise information - tabulate data |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| 4.5. Conduct discussion |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
| 4.6. Create scale for severity |  |  |  | 0% | 2024-02-08 | 2 | 2024-02-10
Reporting Procedure
| 1. Outline step-by-step procedure |  |  |  | 0% | 2024-02-13 | 3 | 2024-02-16
| 1.1 Specify who, where, when, what, how - include action duration & reporting channel |  |  |  | 0% | 2024-02-26 | 3 | 2024-02-29
| 1.2. Discuss information |  |  |  | 0% | 2024-02-19 | 1 | 2024-02-20
| 1.3. Make decision |  |  |  | 0% | 2024-02-19 | 1 | 2024-02-20
| 1.4. Create worklow for reporting procedure |  |  |  | 0% | 2024-02-19 | 1 | 2024-02-20
Investigation Procedure
| 1. Outline investigation process |  |  |  | 0% | 2024-02-29 | 14 | 2024-03-14
| 1.1. Specify who, where, when, what, how |  |  |  | 0% | 2024-02-22 | 7 | 2024-02-29
| 1.2. Find reference for root cause analysis |  |  |  | 0% | 2024-02-29 | 5 | 2024-03-05
| 1.3. Find reference for investigation checklist |  |  |  | 0% | 2024-03-05 | 5 | 2024-03-10
| 1.4. Create workflow for investigation |  |  |  | 0% | 2024-03-05 | 1 | 2024-03-06
| 2. Outline corrective action process |  |  |  | 0% | 2024-03-06 | 5 | 2024-03-11
| 2.1. Specify who, where, when, what, how |  |  |  | 0% | 2024-03-12 | 1 | 2024-03-13
| 2.2. Outline requirement for training |  |  |  | 0% | 2024-03-13 | 1 | 2024-03-14
| 2.3. Outline pre- and post training |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| Roles & Responsibilities |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1. Map out worflow |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1.1. Identify roles |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1.2. Describe responsibilities - develop responsibility matrix |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1.3. Discuss task |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1.4. Delegate task |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 2. Appointment Letter |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 2.1. Draft letter |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 2.2. Review and approve by Director |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| Procedures for Record Keeping |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 1. Specify type of record |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 2. Specify confidentiality level |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 3. Determine authorisation |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 4. Define record storage time frame |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 5. Identify storage space |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
| 6. Outline archival procedures |  |  |  | 0% | 2024-03-14 | 1 | 2024-03-15
Write SOP & forms for accident reporting
| 1. Draft SOP documents |  |  |  | 0% | 2024-03-18 | 35 | 2024-04-22 | 36
| 1.1. Review existing template |  |  |  | 0% | 2024-03-18 | 5 | 2024-03-23
| 1.2. Modify template if needed |  |  |  | 0% | 2024-03-23 | 2 | 2024-03-25
| 1.3. Write SOP |  |  |  | 0% | 2024-03-25 | 14 | 2024-04-08
| 1.4. Check SOP format, spelling |  |  |  | 0% | 2024-04-08 | 3 | 2024-04-11
| 1.5. Finalise draft |  |  |  | 0% | 2024-04-08 | 3 | 2024-04-11
Draft form for accident/incident reporting
| 1. Review existing form |  |  |  | 0% |  |  | 0
| 2. Modify template |  |  |  | 0% | 2024-04-15 | 5 | 2024-04-20
| 3. Design form |  |  |  | 0% | 2024-04-15 | 1 | 2024-04-16
| 4. Check formatting |  |  |  | 0% | 2024-04-20 | 7 | 2024-04-27
| 5. Finalise form |  |  |  | 0% | 2024-04-29 | 3 | 2024-05-02
| Create Survey on SOP |  |  |  | 0% |  |  | 0
| 1. Create template |  |  |  | 0% | 2024-05-06 | 3 | 2024-05-09
| 2. Modify template |  |  |  | 0% | 2024-05-06 | 1 | 2024-05-07
| 3. Design survey |  |  |  | 0% | 2024-05-07 | 1 | 2024-05-08
| 4. Check formatting |  |  |  | 0% | 2024-04-20 | 7 | 2024-04-27
| 5. Finalise survey |  |  |  | 0% | 2024-04-29 | 3 | 2024-05-02
Write SOP & forms for accident investigation
| 1. Draft SOP documents |  |  |  | 0% | 2024-03-18 | 35 | 2024-04-22 | 36
| 1.1. Review existing template |  |  |  | 0% | 2024-03-18 | 5 | 2024-03-23
| 1.2. Modify template if needed |  |  |  | 0% | 2024-03-23 | 2 | 2024-03-25
| 1.3. Write SOP |  |  |  | 0% | 2024-03-25 | 14 | 2024-04-08
| 1.4. Check SOP format, spelling |  |  |  | 0% | 2024-04-08 | 3 | 2024-04-11
| 1.5. Finalise draft |  |  |  | 0% | 2024-04-08 | 3 | 2024-04-11
| 2. Draft Checklist of investigation |  |  |  | 0% | 2024-05-05 | 3 | 2024-05-08 | 4
| 2.1 Design checklist |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 2.2 Write checklist |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 2.3 Check |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 2.4 Finalise checklist |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 3. Draft form |  |  |  | 0% | 2024-05-05 | 3 | 2024-05-08 | 4
| 3.1 Review existing RCA form |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 3.2 Modify form |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 3.3 Write form |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 3.4 Check form |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 3.5 Finalise form |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 4. Create pre- and post-training survey |  |  |  | 0% | 2024-05-05 | 3 | 2024-05-08 | 4
| 1. Create template |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 2. Modify template |  |  |  | 0% | 2024-05-08 | 2 | 2024-05-10
| 3. Design survey |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 4. Check formatting |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
| 5. Finalise survey |  |  |  | 0% | 2024-05-10 | 3 | 2024-05-13
Validate SOP and forms
1. Plan for reading exercise
| 1. Select participant |  |  |  | 0% |  |  | 0
| 2. inform participant |  |  |  | 0% | 2024-05-06 | 1 | 2024-05-07
| 3. Schedule exercise |  |  |  | 0% | 2024-05-06 | 1 | 2024-05-07
| 4. Provide exercise material |  |  |  | 0% | 2024-05-06 | 3 | 2024-05-09
| 5. Conduct exercise |  |  |  | 0% | 2024-05-06 | 1 | 2024-05-07
2. Plan for pilot table-top exercise
| 1. Select participant |  |  |  | 0% |  |  | 0
| 2. inform participant |  |  |  | 0% | 2024-05-07 | 2 | 2024-05-09
| 3. Schedule exercise |  |  |  | 0% | 2024-05-09 | 1 | 2024-05-10
| 4. Prepare exercise material |  |  |  | 0% | 2024-05-09 | 1 | 2024-05-10
| 4.1 Draft exercise material |  |  |  | 0% | 2024-05-10 | 1 | 2024-05-11
| 4.2 Check exercise material |  |  |  | 0% | 2024-06-05 | 3 | 2024-06-08 | 4
| 4.3 Final exercise material |  |  |  | 0% | 2024-06-05 | 3 | 2024-06-08 | 4
3. Conduct pilot-table top exercise
| 1. Deploy pre-assessment survey |  |  |  | 0% | 2024-06-05 | 3 | 2024-06-08
| 2. Execute table top exercise |  |  |  | 0% | 2024-06-05 | 3 | 2024-06-08
| 3. Deploy post-assessment survey |  |  |  | 0% | 2024-06-04 | 3 | 2024-06-07
4. Analyse feedback
| 1. Discuss feedback |  |  |  | 0% | 2024-05-14 | 1 | 2024-05-15 | 2
| 2. Review SOP and form |  |  |  | 0% | 2024-05-13 | 1 | 2024-05-14 | 2
| 3. Modify SOP and form as needed |  |  |  | 0% | 2024-05-14 | 1 | 2024-05-15
5. Finalise SOP and form
| 1. Assign code to SOP document |  |  |  | 0% | 2024-05-16 | 1 | 2024-05-17 | 2
| 2. Assign code to forms |  |  |  | 0% | 2024-05-21 | 7 | 2024-05-28 | 8
6. Verify and approve by IBBC
| 1. Circulate SOP and form to IBBC |  |  |  | 0% | 2024-05-21 | 1 | 2024-05-22
| 2. Register as controlled document |  |  |  | 0% | 2024-05-23 | 3 | 2024-05-26
0
Stretch
| Plan Outreach Program |  |  |  | 0% | 2024-02-11 | 2 | 2024-02-13
| 1. Training |  |  |  | 0% | 2024-02-19 | 14 | 2024-03-04
Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.